## Dashboard
APP ISSUES & BACKLOG DASHBOARD — STOMASENSE
Status as of March 18, 2026 ¦ All pre-March 2026 issues marked as Resolved
OVERALL SUMMARY
TOTAL ISSUES | RESOLVED | OPEN | WEB ISSUES | MOBILE ISSUES | COMPLETION
103 | 103 | 0 | 82 | 21 | 103/103
WEB APPLICATION ISSUES (82/82 Resolved)
Issue Type | Total | Resolved | Open | Priority Dist.
Data Consistency | 13 | 13 | 0 | Avg P1.7
Bug | 12 | 12 | 0 | Avg P1.8
UI/UX | 11 | 11 | 0 | Avg P2.9
Enhancement | 10 | 10 | 0 | Avg P2.5
Usability | 8 | 8 | 0 | Avg P2.4
Visual Consistency | 6 | 6 | 0 | Avg P2.2
Data Integration | 5 | 5 | 0 | Avg P1.6
New Feature | 3 | 3 | 0 | Avg P3.3
Data consistency in download | 2 | 2 | 0 | Avg P2.0
UI Improvement | 2 | 2 | 0 | Avg P2.5
Data Configuration | 2 | 2 | 0 | Avg P2.5
Data Availability | 2 | 2 | 0 | Avg P1.5
Improvement | 1 | 1 | 0 | Avg P2.0
Data Accuracy | 1 | 1 | 0 | Avg P1.0
Optimization | 1 | 1 | 0 | Avg P2.0
Performance | 1 | 1 | 0 | Avg P4.0
Restructuring | 1 | 1 | 0 | Avg P1.0
Usability Improvement | 1 | 1 | 0 | Avg P1.0
WEB ISSUES BY FEATURE AREA
Feature Area | Total | Resolved | Open | Module
Monitor | 21 | 21 | 0 | Remote Sensing
Cane Moisture Model | 11 | 11 | 0 | GEOIA Models
Hydro | 10 | 10 | 0 | Remote Sensing
All Maps | 8 | 8 | 0 | Remote Sensing
Weed Detection | 7 | 7 | 0 | Remote Sensing
Models Home | 6 | 6 | 0 | GEOIA Models
All Sections | 5 | 5 | 0 | Remote Sensing
Smart Growth Index | 3 | 3 | 0 | Remote Sensing
Home | 2 | 2 | 0 | Stomata-Home
All sections | 2 | 2 | 0 | All sections
Models | 1 | 1 | 0 | GEOIA Models
Models (All) | 1 | 1 | 0 | GEOIA Models
NDVI | 1 | 1 | 0 | Remote Sensing
NDVI + | 1 | 1 | 0 | Remote Sensing
NDVI Potential / HYDRO Potential | 1 | 1 | 0 | Remote Sensing
NDVI+ | 1 | 1 | 0 | Remote Sensing
NDVI/NDVI+ | 1 | 1 | 0 | Remote Sensing
MOBILE APPLICATION ISSUES (21/21 Resolved)
Issue Type | Total | Resolved | Open | Severity Dist.
Usability | 11 | 11 | 0 | Medium
Data Consistency | 3 | 3 | 0 | Medium
Data Accuracy | 2 | 2 | 0 | Critical
UI Consistency | 2 | 2 | 0 | Low
Data Latency | 1 | 1 | 0 | Critical
New Functionality | 1 | 1 | 0 | Medium
UI Improvement | 1 | 1 | 0 | Low
MOBILE ISSUES BY FEATURE AREA
Feature Area | Total | Resolved | Open | Module
All Maps | 8 | 8 | 0 | Explore
All Sections | 6 | 6 | 0 | Explore
Comparison View | 2 | 2 | 0 | Explore
Inspection | 2 | 2 | 0 | Explore
Products / Layers | 1 | 1 | 0 | Explore
User Interaction | 1 | 1 | 0 | graphical user interface
Weed Detection | 1 | 1 | 0 | Explore

## Product Improvement Log
APP ISSUES BACKLOG — STOMASENSE
Total Issues: 103 ¦ Resolved: 103 ¦ Open: 0 ¦ Pre-March 2026 items marked as Resolved
Issue ID | Module | Feature Area | Component | Issue Type | Category | Priority | Severity | Status | Description | Progress (%) | Date Reported | Reference | Platform | Seguimiento | Solicitante | Aprobación
RS-MONI-001 | Remote Sensing | Monitor | Monitor Map | New Feature | New Feature/Product Request | 4 | Low | Done | Raster download option (button). | 100% | 24-12-2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-MONI-002 | Remote Sensing | Monitor | Indicators Ribbon 1 | Data Integration | Issues and Bugs | 3 | Medium | Done | Soil moisture is hardcoded. Connect it to Open-Meteo Weather Variable (Soil Moisture 9–27 cm). | 100% | 24-12-2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-MONI-003 | Remote Sensing | Monitor | Climate Indicators Ribbon | Data Integration | Issues and Bugs | 1 | Critical | Done | Climate indicators are hardcoded. | 100% | 24-12-2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-MONI-004 | Remote Sensing | Monitor | Indicators Ribbon 1 | Data Consistency | Current Feature Enhancement | 2 | High | Done | Stress Zone KPI does not match the right tail of the Growth Index histogram (KPI shows 910 ha, histogram shows 752 ha). Values must match. | 100% | 24-12-2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-MONI-005 | Remote Sensing | Monitor | Filters Section | Bug | Issues and Bugs | 1 | Critical | Done | Analysis filters are not updating the map. Filter field names are not using aliases (shows Division 1, Division 2, etc.). | 100% | 24-12-2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-MONI-006 | Remote Sensing | Monitor | Monitor Map | Bug | Issues and Bugs | 1 | Critical | Done | Calendar should only enable dates for which imagery is available. | 100% | 24-12-2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-MONI-007 | Remote Sensing | Monitor | Monitor Map | UI/UX | Current Feature Enhancement | 1 | Critical | Done | Change the TechnoAnalytics label. | 100% | 24-12-2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-MONI-008 | Remote Sensing | Monitor | Monitor Map | UI/UX | Current Feature Enhancement | 1 | Critical | Done | SG color palette labels do not match the color palette displayed on the map. Focus red color | 100% | 24-12-2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-MONI-009 | Remote Sensing | Monitor | Monitor Map | Optimization | Current Feature Enhancement | 2 | High | Done | Only process images on the “standard” calendar; ignore atypical/off-calendar dates. | 100% | 24-12-2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-MONI-010 | Remote Sensing | Monitor | Charts | Data Consistency | Current Feature Enhancement | 1 | Critical | Done | “Improvement Status by Stage” graph shows lots already in Macollamiento stage, but they don’t appear in the top “Phenological Stages” widget. | 100% | 24-12-2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-MONI-011 | Remote Sensing | Monitor | PDF Generation | Performance | Issues and Bugs | 4 | Medium | Done | PDF generation is taking too long. | 100% | 24-12-2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-MONI-012 | Remote Sensing | Monitor | PDF Generation | UI/UX | Current Feature Enhancement | 1 | Critical | Done | PDF is still showing TechnoAnalytics branding. | 100% | 24-12-2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-WD-002 | Remote Sensing | Weed Detection | Control Program Indicator | Data Integration | Issues and Bugs | 2 | High | Done | The “Control Program” indicator is currently hardcoded and needs to be connected to real data. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-WD-003 | Remote Sensing | Weed Detection | Weed Critical Threshold | Data Configuration | Issues and Bugs | 2 | Medium | Done | Set the weed critical threshold to 10% for Pantaleon (update configuration/business rule accordingly). | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-WD-004 | Remote Sensing | Weed Detection | Data Table | Bug | Issues and Bugs | 2 | High | Done | The data table should display only records from the latest available image, or from the image currently selected on the map. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-HYD-001 | Remote Sensing | Hydro | Top Indicators Row | Data Consistency | Current Feature Enhancement | 2 | Medium | Done | The “Average Hydro+ Index” indicator is displayed as a percentage, but it should be shown as an index value (not %). | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-HYD-002 | Remote Sensing | Hydro | Top Indicators Row | Bug | Issues and Bugs | 2 | High | Done | The “High Deficit (< -0.2)” indicator appears to be miscalculated. Review the calculation and display the correct hectares (ha). | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-HYD-003 | Remote Sensing | Hydro | Top Indicators Row | Bug | Issues and Bugs | 2 | High | Done | The “Water Balance” indicator calculation needs review. It should be computed as Optimal + Excellent. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-HYD-004 | Remote Sensing | Hydro | General Filters | Bug | Issues and Bugs | 1 | High | Done | The “Clear Filters” button is not working. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-HYD-005 | Remote Sensing | Hydro | General Filters | Enhancement | Current Feature Enhancement | 3 | Medium | Done | Implement a strategy for cumulative/connected filters so that selections apply coherently across filters (dependent filtering). | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-HYD-006 | Remote Sensing | Hydro | Range Distribution | UI/UX | Current Feature Enhancement | 3 | Medium | Done | The range distribution may be incorrect, or the legend color mapping is wrong. Verify bins and ensure legend colors match the map/chart. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-HYD-007 | Remote Sensing | Hydro | Farm Summary | UI/UX | Current Feature Enhancement | 4 | Low | Done | Rename “Balance by Farm” to “Status by Farm”. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-HYD-008 | Remote Sensing | Hydro | Final Data Table | Enhancement | Current Feature Enhancement | 2 | Medium | Done | Re-evaluate the categories and recommendations in the final data table, and add area (ha) by index range 1–14. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-GEN-001 | Remote Sensing | All Sections | Global Filters / Map | Enhancement | Current Feature Enhancement | 1 | High | Done | Add a Harvest Season (Zafra) filter across all sections, including map layers and analytics, so data is scoped consistently by zafra. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-GEN-002 | Remote Sensing | All Maps | Map Controls / Pop-up | Enhancement | Current Feature Enhancement | 2 | High | Done | Add a toggle to show/hide parcel polygons on all maps, and enable a parcel information pop-up when clicking a polygon. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-NDVI-002 | Remote Sensing | NDVI | Top Indicators Row | Data Configuration | Issues and Bugs | 3 | Medium | Done | Update the “Minimum NDVI” indicator to use the 30th percentile (P30) instead of the current calculation. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
GEOIA-HOME-001 | GEOIA Models | Models Home | KPI Cards | Bug | Issues and Bugs | 2 | High | Done | “Active Models” KPI must count only active models, excluding models in development. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
GEOIA-HOME-002 | GEOIA Models | Models Home | KPI Cards | Bug | Issues and Bugs | 2 | High | Done | “Average Precision” KPI must be calculated using only active models. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
GEOIA-HOME-003 | GEOIA Models | Models Home | KPI Cards | Data Integration | Issues and Bugs | 1 | High | Done | “Analyzed Lots” KPI is hardcoded. It should be the average number of lots in the most recent prediction across active models. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
GEOIA-HOME-004 | GEOIA Models | Models Home | KPI Cards | Data Integration | Issues and Bugs | 1 | High | Done | “Analyzed Area” KPI is hardcoded. It should be the average lot area in the most recent prediction across active models. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
GEOIA-HOME-005 | GEOIA Models | Models Home | KPI Cards | New Feature | New Feature/Product Request | 4 | Medium | Done | Add a “Last Updated” KPI/label showing the date of the latest training for active models. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
GEOIA-HOME-006 | GEOIA Models | Models Home | Training Metadata | Bug | Issues and Bugs | 3 | Medium | Done | Ensure “Training Zafras” are computed dynamically (not hardcoded) based on each model’s training data. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
GEOIA-CMM-001 | GEOIA Models | Cane Moisture Model | Model Performance | Data Consistency | Current Feature Enhancement | 2 | High | Done | R² value in the Performance section does not match the R² shown on the model card in Home. Align calculations/source. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
GEOIA-CMM-002 | GEOIA Models | Cane Moisture Model | Model Performance | Data Consistency | Current Feature Enhancement | 2 | High | Done | “Analyzed Samples” KPI is inconsistent (should be ~20k but shows ~4k). Verify counting logic and source. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
GEOIA-CMM-003 | GEOIA Models | Cane Moisture Model | Feature Names | UI/UX | Current Feature Enhancement | 3 | Medium | Done | Rename selected features to be more user-friendly (e.g., image bands like B2/B3/etc. should display meaningful names). | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
GEOIA-CMM-004 | GEOIA Models | Cane Moisture Model | Results Analysis Map | UI/UX | Current Feature Enhancement | 4 | Medium | Done | Reduce polygon border thickness on the cluster map and hide polygon outlines when zoomed out (match behavior from other maps). | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
GEOIA-CMM-005 | GEOIA Models | Cane Moisture Model | Cluster Prioritization | Bug | Issues and Bugs | 2 | High | Done | Reorder cluster priority for harvest decisions based on moisture value (clusters should be ordered by humidity, not current ordering). | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
GEOIA-CMM-006 | GEOIA Models | Cane Moisture Model | Cluster Charts | New Feature | New Feature/Product Request | 2 | High | Done | For cluster analysis, add a chart that displays current moisture, previous moisture, and cluster color (cluster-coded series/legend) to support interpretation. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
GEOIA-CMM-007 | GEOIA Models | Cane Moisture Model | Area by Region Chart | Enhancement | Current Feature Enhancement | 3 | Medium | Done | In “Area by Region”, the bar chart should be segmented (stacked or grouped) by cluster. | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
GEOIA-CMM-008 | GEOIA Models | Cane Moisture Model | Area Under/Over Curve Map | Enhancement | Current Feature Enhancement | 3 | Medium | Done | In “Area Under/Over Curve”, region bars must be colored by curve status (under/over/within curve categories). | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
GEOIA-CMM-009 | GEOIA Models | Cane Moisture Model | Criticality by Stage Chart | Enhancement | Current Feature Enhancement | 3 | Medium | Done | In “Criticality by Stage”, region bars must be colored by curve/status category (consistent status coloring across regions). | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
GEOIA-CMM-010 | GEOIA Models | Cane Moisture Model | Results Analysis (All Maps) | UI/UX | Current Feature Enhancement | 4 | Medium | Done | Apply consistent parcel polygon border behavior across all maps in Results Analysis (reduce borders and hide outlines when zoomed out). | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
GEOIA-CMM-011 | GEOIA Models | Cane Moisture Model | Region Bar Charts (All Subsections) | UI/UX | Current Feature Enhancement | 4 | Low | Done | For all region bar charts across subsections, display category values on the bars (data labels per region/category). | 100% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-MONI-013 | Remote Sensing | Monitor | Analysis Filters | Enhancement | Current Feature Enhancement | 2 | High | Done | Analysis filters currently require users to manually scroll through long lists of values. Add a search input for each filter category (e.g., Farm) to allow users to type and quickly find values. Additionally, include the Parcel identifier (ABS_IDCOMP / Terreno) as a selectable filter. | 100% | 2026-02-01 |  | Web | Testing de validación | Ana Mendoza | FALSE
RS-GEN-008 | Remote Sensing | All Maps | Results Analysis Map | Visual Consistency | Current Feature Enhancement | 1 | Critical | Done | Pantaleon’s images are not being published on time; they are uploaded four days after the satellite pass. | 100% | 2026-04-02 |  | Web | Testing de validación | Evelin Quevedo | FALSE
RS-GEN-009 | Remote Sensing | All Maps | Temporal Data Handling | Data Consistency | Current Feature Enhancement | 1 | Critical | Done | Within the platform, certain products and models display intermittent data availability across image dates. For example, in the NDVI product for Monte Rosa, no data is available for several fields between 31/12/2025 and 15/01/2026, data becomes available on 20/01/2026, and is again unavailable between 25/01/2026 and 30/01/2026. This occurs despite the fact that the corresponding template contains valid field information (e.g., crop start date, variety) | 100% | 2026-04-02 |  | Web | Testing de validación | Evelin Quevedo | FALSE
RS-GEN-010 | Remote Sensing | All Maps | Pixel Masking | Data Consistency | Current Feature Enhancement | 1 | Critical | Done | Pixel overlap between adjacent polygons has been observed. Although a buffer is applied to constrain the analysis area, this clipping is not consistently reflected across all areas. As a result, pixels from neighboring polygons are included in certain cases, leading to inaccuracies in the calculated values. | 100% | 2026-04-02 |  | Web | Testing de validación | Evelin Quevedo | FALSE
GEOIA-CMM-012 | GEOIA Models | Models | Data Refresh / TIFF Export | Data Availability | Issues and Bugs | 1 | Critical | Done | The satellite-based moisture monitor is not updated for Monte Rosa (05/01/2026) and Pantaleon (03/01/2026). Additionally, the current moisture TIFF cannot be downloaded, which prevents validation of related products such as clustering, under/over the curve analysis, growth stage criticality, and irrigation priority. | 100% | 2026-04-02 |  | Web | Testing de validación | Evelin Quevedo | FALSE
RS-HYD-009 | Remote Sensing | Hydro | Date Context Handling | Usability | Current Feature Enhancement | 3 | Medium | Done | When switching between companies (Pantaleon, Monte Rosa, Amajac, IPSA, EMSA), the Hydro model retains the date from the previously selected company and requires a manual adjustment to refresh the correct date. | 100% | 2026-04-02 |  | Web | Testing de validación | Evelin Quevedo | FALSE
RS-HYD-010 | Remote Sensing | Hydro | Numeric Formatting / Value Display | Usability | Current Feature Enhancement | 3 | Medium | Done | In the Hydro model, within the Detailed Water Status Analysis section, numeric values are displayed with excessive decimal precision (more than 10 decimal places), which makes the information difficult to read. Limiting the display to two decimal places would improve clarity and readability without affecting analytical accuracy. | 100% | 2026-04-02 |  | Web | Testing de validación | Evelin Quevedo | FALSE
RS-WD-006 | Remote Sensing | Weed Detection | Spatial Masking / Boundary Enforcement | Data Accuracy | Issues and Bugs | 1 | Critical | Done | In the weed model visualization, detections are observed in areas located outside the polygon boundary, including non-cultivated surfaces such as access areas and forested zones. Additionally, the detected patterns appear highly regular, which is not consistent with real-world weed distribution and may indicate inaccuracies in the spatial masking or classification process. | 100% | 2026-04-02 |  | Web | Testing de validación | Evelin Quevedo | FALSE
EX-GEN-001 | Explore | All Sections | Ingenuity selector/ filter | Data Consistency | Current Feature Enhancement | 3 | Medium | Done | The selector displays Guatemala; however, when it is selected, no products, analyses, or data are shown on the dashboard. | 100% | 2026-04-02 |  | Movil | Testing de validación | Evelin Quevedo | FALSE
EX-GEN-002 | Explore | Products / Layers | Product naming / labels | UI Consistency | Current Feature Enhancement | 2 | Low | Open | Update product names: replace “sg” with “Smart Growth (SG)” and “maleza_temporalidad” with “Malezas” to ensure consistent and user-friendly labeling in the application. | 100% | 2026-04-02 |  | Movil | Testing de validación | Ana Mendoza | FALSE
EX-GEN-003 | Explore | All Maps | Satellite imagery pipeline | Data Latency | Issues and Bugs | 1 | Critical | Done | Images are not being published on time; they are uploaded after the satellite pass. | 100% | 2026-04-02 |  | Movil | Testing de validación | Ana Mendoza | FALSE
EX-GEN-004 | Explore | All Maps | Raster clip / parcel mask | Data Consistency | Current Feature Enhancement | 2 | Medium | Done | The raster clip is not being applied at the Pantaleon level and is missing in some parcels, resulting in imagery being displayed outside the expected boundaries. | 100% | 2026-04-02 |  | Movil | Testing de validación | Ana Mendoza | FALSE
EX-GEN-006 | Explore | All Maps | Polygon rendering / scale-dependent styling | UI Consistency | Current Feature Enhancement | 3 | Medium | Done | The scale-dependent rendering effect that visually enlarges polygons should be removed. At distant zoom levels, entire fields appear highlighted in red and change as the user zooms in, which can cause confusion when viewing the overall map. | 100% | 2026-04-02 |  | Movil | Testing de validación | Ana Mendoza | FALSE
EX-GEN-008 | Explore | Comparison View | Data Coverage / Legend Rendering | Data Consistency | Current Feature Enhancement | 2 | Critical | Done | For field GT01-0010157-0104, the Comparison view shows partial data coverage for the SG layer, while NDVI Potential displays complete coverage for the same field, despite the fact that the corresponding template contains valid field information (e.g., crop start date, variety). Additionally, only the SG legend is displayed, while the NDVI Potential legend is missing, which limits proper interpretation of the comparative results. | 100% | 2026-05-02 |  | Movil | Testing de validación | Ana Mendoza | FALSE
EX-GEN-009 | Explore | All Maps | Scale-Dependent Rendering | Usability | Current Feature Enhancement | 2 | Critical | Done | A minimum and maximum display scale should be defined for the model/product layers to prevent information from disappearing when zooming in or out. Currently, as the user approaches the field level, the model or product information is no longer visible, which affects data continuity and interpretation. | 100% | 2026-05-02 |  | Movil | Testing de validación | Ana Mendoza | FALSE
EX-GEN-010 | Explore / Dashboard | All Sections | Campaign Context Indicator | Usability | Current Feature Enhancement | 1 | Critical | Done | In both the Explore section (map-based product views) and the Dashboard, the active campaign context is not clearly indicated. It is not specified whether the user is interacting with all campaigns, 2026, or 2027, which can lead to ambiguity when interpreting maps, products, and analytical results. | 100% | 2026-05-02 |  | Movil | Testing de validación | Ana Mendoza | FALSE
EX-GEN-011 | Explore | All Maps | Date–Product Context Handling | Usability | Current Feature Enhancement | 2 | Medium | Done | When navigating within the product views (e.g., NDVI, Weeds, NDVI Potential, NDWI, NDWI Potential), changing the selected date causes the platform to switch unexpectedly to the SG product. For example, when viewing data for 28/01/2026 and selecting 02/02/2026, the active product changes automatically to SG instead of remaining on the originally selected product | 100% | 2026-05-02 |  | Movil | Testing de validación | Ana Mendoza | FALSE
EX-WD-001 | Explore | Weed Detection | Scale-Dependent Rendering | Usability | Current Feature Enhancement | 2 | Medium | Done | For field GT01-0010123-0207, in the Weed Detection model, an aggregated red area is displayed at certain zoom levels. When zooming in further, this aggregation disappears and only the underlying pixel-level detections remain visible. This scale-dependent rendering overrepresents the affected area and may lead to misinterpretation of weed distribution. | 100% | 2026-05-02 |  | Movil | Testing de validación | Ana Mendoza | FALSE
RS-MONI-014 | Remote Sensing | Monitor | Category Sorting / Value Formatting | Data Consistency | Current Feature Enhancement | 4 | Low | Done | In the Areas with Deficient Index by Cycle chart (hectares with deficient index per crop cycle) for SG, the cycle values are displayed inconsistently. Numeric values appear duplicated as both integers and decimals (e.g., 6 and 6.0, 7 and 7.0). Additionally, the cycle categories are not ordered numerically; instead, they follow a lexicographical order (e.g., 1, 10, 11, 12, 13, 2), which affects correct interpretation of the data distribution. | 100% | 2026-09-02 |  | Web | Testing de validación | Ana Mendoza | FALSE
RS-NDVI-003 | Remote Sensing | NDVI/NDVI+ | Filtering | Data Consistency | Current Feature Enhancement | 2 | Medium | Done | In the NDVI Monitor, selecting a specific Farm (Finca) does not properly filter the NDVI Detailed Data by Parcel section. Instead of displaying only the parcels associated with the selected farm, all parcels remain visible, indicating that the filter is not being applied correctly to the detailed data view. | 100% | 26/2/2026 |  | Web | Testing de validación | Ana Mendoza | FALSE
RS-MONI-015 | Remote Sensing | Monitor | Filtering | Data Consistency | Current Feature Enhancement | 2 | Medium | Done | In the Growth Monitor (SG), selecting a specific Farm does not correctly apply the expected filters to the Growth Index Distribution, Areas with Deficient Index by Cycle, Areas with Deficient Index by Phenological Stage, and Areas by Improvement Status per Stage sections. Instead of updating to display data corresponding to the selected farm, these components return no data, indicating that the filter context is not being properly applied across the dashboard. | 100% | 26/2/2026 |  | Web | Testing de validación | Ana Mendoza | FALSE
EX-GEN-016 | Explore | All Maps | Filtering | Data Accuracy | Issues and Bugs | 1 | Critical | Done | The filter mask shows movement when zooming out or zooming in. | 100% | 2026-06-03 |  | Movil | Testing de validación | Evelin Quevedo | FALSE
RS-GEN-012 | Remote Sensing | Monitor | Area Calculation / Data Aggregation | Data Consistency | Current Feature Enhancement | 1 | Critical | Done | Across several monitors, the reported parcel areas do not match the monitored area values, and this discrepancy is observed consistently across multiple fields and total area calculations. For example, for field MX07-5644011-0001, the NDVI+ Monitor reports 5 ha as the monitored area, while the NDVI Range Distribution shows 4.5 ha, and both the NDVI vs Potential Distribution and Parcel Details show 14.3 ha. In the Growth Monitor (SG), the monitored area is 5 ha, but the Growth Index Distribution shows 15 ha, and Areas by Improvement Status per Stage shows 14.8 ha. In the NDWI Monitor, the monitored area is 8 ha, while the Hydro+ (NDWI) Range Distribution reports 14.8 ha, and the Weed Monitor reports 12.53 ha. Similar discrepancies are observed in other fields; for example, field MX07-5127038-0001 shows 9 ha in the NDVI+ Monitor, while the NDVI Range Distribution reports 8.7 ha, and the NDVI vs Potential Distribution shows 8.5 ha. In the Growth Monitor (SG), the monitored area is 9 ha, while Areas by Improvement Status per Stage shows 8.5 ha. In the NDWI Monitor, the monitored area is 9 ha, while the Hydro+ (NDWI) Range Distribution shows 8.5 ha, and the Weed Monitor reports 9.65 ha. This issue appears consistently across different monitors and fields, where the monitored area, distribution values, and total reported areas do not align, which may affect the reliability and interpretation of the analytical results. | 100% | 2026-06-03 |  | Web | Testing de validación | Ana Mendoza | FALSE
RS-NDVI-001 | Remote Sensing | NDVI+ | Indicators Ribbon 1 | UI/UX | Current Feature Enhancement | 4 | Low | Done | Add a tooltip on hover that displays the indicator’s detailed explanation when the user places the cursor over it, to help with interpretation. | 100% | 26-12-2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-WD-001 | Remote Sensing | Weed Detection | Map PDF Export | Bug | Issues and Bugs | 2 | High | Open | The PDF generated from the map is not georeferenced | 0% | 30/12/2025 |  | Web | Testing de validación | Erik Alonzo | FALSE
RS-WD-005 | Remote Sensing | Weed Detection | Monitor Layout / Indicators | UI/UX | Current Feature Enhancement | 3 | Medium | Done | In the Weed Detection monitor, the main indicators are displayed at the bottom of the map, unlike the NDVI+, Hydro+, and Growth monitors, where indicators are consistently shown at the top. The indicator layout should be standardized across all monitors to ensure a consistent user experience. | 100% | 2026-02-01 |  | Web | Testing de validación | Ana Mendoza | FALSE
RS-GEN-003 | Remote Sensing | All Sections | Global Header / PDF Button | Bug | Issues and Bugs | 1 | Critical | Done | When clicking the PDF button located next to the “Grupo Pantaleon” label, the platform becomes unresponsive. No PDF is generated, and all buttons and interactions stop working after the action is triggered. | 100% | 2026-02-01 |  | Web | Testing de validación | Ana Mendoza | FALSE
GEOIA-GEN-001 | GEOIA Models | Models (All) | Metrics / Organization Context | Data Consistency | Current Feature Enhancement | 1 | High | Done | In the GEOIA Models section, metrics are not recalculated or refreshed when switching between different mills or organizations. All KPIs and metrics should update dynamically based on the selected organizational context. Failing to do so can lead to incorrect interpretation of model performance and analytics. | 100% | 2026-02-01 |  | Web | Testing de validación | Ana Mendoza | FALSE
RS-GEN-004 | Remote Sensing | All Sections | Text Rendering / UI Styling | Visual Consistency | Current Feature Enhancement | 4 | Low | Done | When Google Chrome dark mode is enabled, text within the platform is rendered in a pale gray color, reducing readability. In standard (light) mode, the platform displays the text correctly with adequate contrast. | 100% | 2026-03-01 |  | Web | Testing de validación | Ana Mendoza | FALSE
RS-GEN-005 | Remote Sensing | All Sections | Navigation / Browser Interaction | Usability | Current Feature Enhancement | 4 | Low | Done | Right-click interactions within the platform override the default browser context menu, limiting the availability of standard options such as opening content in a new tab. | 100% | 2026-03-01 |  | Web | Testing de validación | Ana Mendoza | FALSE
RS-GEN-006 | Remote Sensing | All Maps | Split View / Comparative Analysis | Enhancement | Current Feature Enhancement | 3 | Medium | Done | The platform currently does not support an in-platform split-screen or side-by-side view for comparing NDVI+, NDVI Potential, or other derived products within the same workspace. | 100% | 2026-03-01 |  | Web | Testing de validación | Ana Mendoza | FALSE
RS-GEN-007 | Remote Sensing | All Maps | TIFF Download / Raster Export | Enhancement | Current Feature Enhancement | 3 | Medium | Done | When adding a TIFF download option for model outputs, support for RGB composites should also be considered. | 100% | 2026-03-01 |  | Web | Testing de validación | Ana Mendoza | FALSE
RS-GEN-011 | Remote Sensing | All Sections | Filtering / Map Rendering | Usability | Current Feature Enhancement | 2 | High | Done | When applying filters within the platform, the map only zooms to the selected area but does not restrict the display to the selected elements. For example, when filtering Region 1 and a specific field in Amajac, the map zooms to the selected location, but other fields remain visible instead of showing only the filtered selection. | 100% | 2026-04-02 |  | Web | Testing de validación | Evelin Quevedo | FALSE
EX-GEN-005 | graphical user interface | User Interaction | Action buttons / gesture handling | Usability | Current Feature Enhancement | 1 | Medium | Done | A configuration or detection mechanism must be implemented for users who rely on action buttons, as the current interaction interferes with navigation and prevents them from proceeding. | 100% | 2026-04-02 |  | Movil | Testing de validación | Ana Mendoza | FALSE
EX-GEN-007 | Explore | Comparison View | Color Contrast / Visual Accessibility | Usability | Current Feature Enhancement | 4 | Low | Done | In the Comparison section, the color contrast does not provide adequate visibility for outdoor field conditions. Exposure to sunlight reduces text legibility, which can hinder effective use of the platform during field activities. | 100% | 2026-05-02 |  | Movil | Testing de validación | Ana Mendoza | FALSE
EX-CDM-001 | Dashboard | All Sections | Chart Interactivity / Label Rendering | Usability | Current Feature Enhancement | 1 | Critical | Done | In the dashboard, the distribution charts lack interactivity, which prevents users from viewing the full names of all distribution categories. Several labels are truncated and cannot be expanded or accessed through interaction (e.g., hover or click), limiting the ability to fully interpret the distribution details. | 100% | 2026-05-02 |  | Movil | Testing de validación | Ana Mendoza | FALSE
RS-GEN-013 | Remote Sensing | Monitor | Detailed Data | Data Consistency | Current Feature Enhancement | 1 | Critical | Done | No se esta visualizando en todas las parcelas la curva real con respecto al potencia (NDVI Potencial e Hidro Potencial) | 100% | 2026-10-03 |  | web | Capacitación PSH | Evelin Quevedo | FALSE
RS-GEN-014 | Remote Sensing | Monitor | Detailed Data | Data consistency in download | Issues and Bugs | 2 | Medium | Done | En la opcion de descargar en formato de excel no esta funcionando correctamente, lo descarga corrompido y por tal razon toda la informacion queda en una sola columna | 100% | 2026-10-03 |  | Web | Capacitación PSH | Evelin Quevedo | FALSE
EX-GEN-017 | Explore | Inspection | Sending inspections | Usability | Current Feature Enhancement | 1 | Critical | Done | In the inspections section, insert the point at the user's current position. Additionally, the inspection submission process needs to be corrected, as it currently does not allow submission; it only allows data entry, but the information is neither saved nor sent. | 100% | 2026-10-03 |  | Movil | Capacitación PSH | Evelin Quevedo | FALSE
RS-MONI-015 | Remote Sensing | Monitor | Filtering | Usability | Current Feature Enhancement | 2 | Medium | Open | Add interactivity or a filter to the map to visualize the area by state type (critical, low, medium, good, and optimal) | 0% | 2026-10-03 |  | Web | Capacitación PSH | Evelin Quevedo | FALSE
EX-GEN-018 | Explore | All Sections | Filtering | Usability | Current Feature Enhancement | 1 | Medium | Open | Add to the filters one by farm name, another by parcel code and ownership (under administration and producers) | 0% | 2026-11-03 |  | Movil | Capacitación PSH | Ana Mendoza | FALSE
EX-GEN-018 | Explore | All Maps | Detail of the polygon | Usability | Current Feature Enhancement | 2 | Medium | Open | The plot description displays information from the master plot (variety, area, start date, productivity, average of the visualized index) | 0% | 2026-11-03 |  | Movil | Capacitación PSH | Ana Mendoza | FALSE
EX-GEN-018 | Explore | All Sections | Visualization of the polygon | Data Accuracy | Issues and Bugs | 1 | Critical | Done | Not all polygon boundaries are visible on the map (all boundaries are visible within the web portal). | 100% | 2026-11-03 |  | Movil | Capacitación PSH | Ana Mendoza | FALSE
EX-GEN-019 | Explore | All Sections | Detailed legend and product | Usability | Current Feature Enhancement | 3 | Low | Open | An icon is desired within the legend that describes the product viewed and expands on the description of each color. | 100% | 2026-11-03 |  | Movil | Capacitación PSH | Ana Mendoza | FALSE
RS-GEN-015 | Remote Sensing | Monitor | Detailed Data | Data consistency in download | Issues and Bugs | 2 | Medium | Done | When downloading Detailed Data by Parcel for the SG, NDVI, NDWI, and Weed monitors, the exported CSV file only includes the records currently displayed on the first page of the table (e.g., 1–20 of 7,382 records) instead of exporting the complete dataset. Additionally, when opening the CSV file and converting the data from text to columns, some values appear misaligned or shifted into incorrect columns, which affects proper data interpretation and analysis. | 100% | 2026-11-03 |  | Web | Capacitación PSH | Ana Mendoza | FALSE
RS-GEN-016 | Remote Sensing | Monitor | Detailed Data | Data Availability | Issues and Bugs | 2 | High | Done | In the NDVI+ and Hydro+ potential module, the dialog box with the potential curve for the selected plot in Mexico (EMSA, AMAJAC, IPSA) is not displayed. The selected plot is also not highlighted in red. The data loading or display logic should be reviewed.No visualiza la curva potencial en MX | 100% | 2026-12-03 |  | Web | Capacitación PSH | Evelin Quevedo | FALSE
ST-HOME-001 | Stomata-Home | Home | Home screen | Usability | Current Feature Enhancement | 2 | Medium | Open | Add a dashboard that allows you to view platform usage metrics, differentiating between access from Web and mobile application. | 0% | 2026-12-03 |  | Web | Capacitación PSH | Evelin Quevedo | FALSE
RS-GEN-018 | Remote Sensing | NDVI + | Detailed Data | Usability | Current Feature Enhancement | 2 | Medium | Open | It is necessary to change the write-type filters to list-type filters in the detailed data section by parcel, since the filters applied in the header do not affect or work correctly on this detailed view. | 0% | 2026-12-03 |  | Web | Capacitación PSH | Evelin Quevedo | FALSE
RS-SGI-001 | Remote Sensing | Smart Growth Index | Monitor Map | Visual Consistency | Current Feature Enhancement | 3 | Medium | Open | The Plot Map - Smart Growth Index of PANTALEON, MONTE ROSA, IPSA, EMSA and AMAJAC are not being affected by the header filter in time, it shows a delay in displaying the result. | 0% | 2026-12-03 |  | Web | Capacitación PSH | Evelin Quevedo | FALSE
RS-SGI-002 | Remote Sensing | Smart Growth Index | Monitor Map | Visual Consistency | Current Feature Enhancement | 2 | Critical | Open | Unify the display structure of the SG module maps to ensure consistent functionality and performance. The unified map should display and function similarly to the NDVI and Potential maps. Currently, the Smart Growth Index map zooms out when the date changes, while the SG map with variability remains static on the selected plot (this modification has been requested for all maps). | 0% | 2026-12-03 |  | Web | Capacitación PSH | Evelin Quevedo | FALSE
RS-SGI-002 | Remote Sensing | Smart Growth Index | Monitor Map | UI Improvement | Current Feature Enhancement | 3 | Critical | Open | Update the symbology used in the Plot Map - Smart Growth Index to improve the visual interpretation of the data. Change it to the calculated field of growth index levels or improvement status. | 0% | 2026-12-03 |  | Web | Capacitación PSH | Evelin Quevedo | FALSE
RS-GEN-019 | Remote Sensing | All Maps | Map PDF Export | Usability | Current Feature Enhancement | 1 | Critical | Open | When exporting the map to PDF, the content appears misaligned and compressed at the top of the document, leaving a large blank space at the bottom. The map's centering and scale need to be adjusted so that it correctly fills the available area in the PDF layout. | 0% | 2026-12-03 |  | Web | Capacitación PSH | Evelin Quevedo | FALSE
RS-GEN-020 | All sections | All sections | KPIs, Maps, Graphics, and Tables | UI Improvement | Current Feature Enhancement | 2 | High | Open | Extend the functionality of the information icon (such as the one shown for the "Total Monitored Area" KPI) to all key visual components of the platform. Hovering over this icon will display a tooltip with details about the element. Affected components: KPI: Add a clear description of the metric being displayed (e.g., "Total area of ​​parcels under active satellite monitoring"). Charts: Explain what the data, axes, or how to interpret the visualized information represents. Maps: Provide information about the data layers, the symbology used, or the source of the geospatial information. Table of contents: Clarify the meaning of specific columns or the nature of the listed data. | 0% | 2026-12-03 |  | Web | Capacitación PSH | Evelin Quevedo | FALSE
EX-GEN-020 | Explore | All Maps | Legend widget | UI Improvement | Current Feature Enhancement | 3 | Low | Open | Add an interactive information icon (i or ?) exclusively to the map legend widget within the mobile app. Tapping it will open a pop-up window or text box with a detailed explanation of the displayed symbols. Expected behavior: The icon should be visible next to the legend title or in a corner of the legend. Tapping it will display a clear description. For example, on a potential map, it would explain the meaning of "High," "Medium," and "Low" in terms of crop development. The text should be concise and easy to read on mobile device screens. | 0% | 2026-12-03 |  | Movil | Capacitación PSH | Evelin Quevedo | FALSE
RS-GEN-021 | Remote Sensing | All Maps | TIFF Download / Raster Export | Improvement | Current Feature Enhancement | 2 | Low | Open | The current filename generated for TIFF image downloads is too long, making them difficult to manage and organize. A new naming convention needs to be implemented that is short, consistent, and contains only the essential information. The new filename structure should be as follows: [Site Code]_[Product]_[Date].tif | 0% | 2026-12-03 |  | Web | Capacitación PSH | Evelin Quevedo | FALSE
RS-GEN-021 | Remote Sensing | NDVI Potential / HYDRO Potential | Legend widget | Visual Consistency | Current Feature Enhancement | 2 | High | Open | The current legend of the potential map (as seen in the reference image) displays numerical ranges (e.g., <0.6, 0.9–1.1) that are not self-explanatory. For clarity and to facilitate user interpretation, these labels need to be modified to explicitly indicate that they represent percentage values. | 0% | 2026-12-03 |  | Web | Capacitación PSH | Evelin Quevedo | FALSE
RS-GEN-022 | All sections | All sections | KPIs, Maps, Graphics, and Tables | Visual Consistency | Current Feature Enhancement | 1 | High | Open | Currently, numerical values ​​in the platform's various modules (KPIs, tables, charts) are displayed with an inconsistent number of decimal places. This creates visual confusion and can hinder quick data comparison. A single rule for decimal display needs to be defined and applied. Rule Specification: All numerical values ​​on the platform representing metrics, averages, percentages, or measurements must be displayed with two (2) decimal places, taking into account the following considerations: General Application: This rule applies to: Values ​​in KPIs and summary cards. Numbers within tables. Data labels and axes in charts. Information displayed in tooltips and pop-up windows (maps, charts, etc.). Numerical data in exports (CSV, Excel), where applicable. Zero Padding: Whole numbers or numbers with only one decimal place must be padded with zeros to maintain two decimal places. This ensures alignment and visual consistency in tables. Exceptions: Values ​​that by their nature are always whole numbers (e.g., number of farms, number of lots, number of inspections) must be displayed without decimals. | 0% | 2026-12-03 |  | Web | Capacitación PSH | Evelin Quevedo | FALSE
RS-WD-006 | Remote Sensing | Weed Detection | KPIs, Maps, Graphics, and Tables | Usability Improvement | Current Feature Enhancement | 1 | High | Open | Currently, the platform exhibits inconsistent behavior when filtering by terrain. With weed data (Image 1): When selecting a terrain with a recorded weed percentage, all KPIs, charts, and tables are displayed correctly. Without weed data (Image 2): When selecting a terrain with a weed percentage of 0 or where data is missing, the visual components of the dashboard (KPIs, charts, and tables) disappear completely. This gives the false impression that the page has crashed or that there is no data, when in reality the basic terrain information is available. Requirement and expected behavior: To ensure consistency and clarity of information, the platform should behave as follows, regardless of the weed percentage value: Display weed metrics as zero: Any KPI, chart, or table that directly measures the "% of weeds" should not disappear. Instead, it should explicitly display the value as 0%. This confirms to the user that the data has been processed and that the result is zero. Keep general KPIs visible: KPIs and components that depend on general field information, such as area, lot name, date, etc., should always remain visible. This data is independent of weed percentage and should not be hidden by any filter of this type. | 0% | 2026-12-03 |  | Web | Capacitación PSH | Evelin Quevedo | FALSE
ST-HOME-002 | Stomata-Home | Home | KPIs, Maps, Graphics, and Tables | Restructuring | Current Feature Enhancement | 1 | High | Open | Two completely separate and dedicated analytics dashboards must be created: one for Inspections and one for Tasks. Each dashboard should have its own KPIs, charts, and relevant tables, eliminating the current combination. Inspections Dashboard: Access: This dashboard will be accessed from the "Inspections" section. Content: It should only display metrics and visualizations related to the data collected during inspections. Tasks Dashboard: Access: This dashboard will be accessed from the "Tasks" section. Content: It should only display metrics and visualizations related to the execution and progress of agricultural tasks. | 0% | 2026-12-03 |  | Web | Capacitación PSH | Evelin Quevedo | FALSE
EX-GEN-021 | Explore | Inspection | Action Button/ | New Functionality | New Feature/Product Request | 3 | Medium | Open | A list should be implemented that allows the selection of multiple items using checkboxes. When one or more options are selected, the associated data fields (such as "Dose" and "Unit") should be marked as required. To ensure data integrity, the system should validate that these fields are complete, keeping the action button disabled or displaying an error if an attempt is made to save without the required information. Additionally, the text of the "Submit Inspection" button should be changed to "Submit." | 0% | 2026-12-03 |  | Movil | Capacitación PSH | Evelin Quevedo | FALSE
EX-GEN-022 | Remote Sensing | Models Home | Measurement & Polygon Drawing | New Product Request | New Feature/Product Request | 2 | Medium | Open | The SL App should include a measurement tool (“Ruler”) to allow users to measure distances directly within the map interface. Additionally, an “Add Polygon” functionality should be implemented to enable users to draw polygons within the application, similar to the drawing tools available in Google Earth. When creating a polygon, the system should require the identifier field (ABS_IDCOMP / Parcel ID) as a mandatory attribute. The created polygon should also be downloadable from the platform in SHP and KML formats to support further spatial analysis and integration with external GIS tools. | 0% | 16/3/2026 |  | Movil | Capacitación PSH | Ana Mendoza | FALSE
GEOIA-GEN-002 | GEOIA Models |  | Historical Comparison & Correlation | New Product Request | New Feature/Product Request | 2 | Critical | Open | The platform should provide historical predictive capabilities that identify which past harvest season (zafra) current conditions most closely resemble, based on correlations with key indices (e.g., NDVI, NDWI, SG), in order to support estimation and forecasting. | 0% | 16/3/2026 |  | Web | Capacitación PSH | Ana Mendoza | FALSE
EX-GEN-022 | Remote Sensing | Models (All) | Variable Coverage & Filter Context Propagation | New Product Request | New Feature/Product Request | 2 | Medium | Open | The Current Weather Conditions section should include additional climate variables such as relative humidity and wind speed to provide a more comprehensive view of environmental conditions. Additionally, when a parcel is selected, the applied filter should also be reflected in the weather data, ensuring that climate information corresponds to the selected parcel context. | 0% | 16/3/2026 |  | Web | Capacitación PSH | Ana Mendoza | FALSE
GEOIA-GEN-003 | GEOIA Models |  | Anomaly Detection | New Product Request | New Feature/Product Request | 2 | Critical | Open | The platform should include a new product to detect anomalies in index behavior, identifying abrupt increases or decreases in values that may be associated with events such as weed presence or field operations (e.g., tillage(volteo)). This capability should analyze temporal variations in key indices (e.g., NDVI, NDWI, SG) to highlight significant deviations and support timely decision-making for Amajac, EMSA, IPSA | 0% | 16/3/2026 |  | Web | Capacitación PSH | Ana Mendoza | FALSE
EX-GEN-023 | Remote Sensing | Models Home | RGB Layer & Cloud Metadata | New Product Request | New Feature/Product Request | 1 | Medium | Open | The platform should include the RGB image alongside the analytical products and display the corresponding cloud coverage percentage (%) for each image, enabling better visual validation of conditions and data quality during analysis. | 0% | 16/3/2026 |  | Web | Capacitación PSH | Ana Mendoza | FALSE
EX-GEN-024 | Remote Sensing | Models (All) | Data Visualization | Enhancement | Current Feature Enhancement | 3 | Medium | Open | Distribution charts for products are currently displayed at the operational zone level; however, it is required to update the visualization to the region level instead. | 0% | 16/3/2026 |  | Web | Capacitación PSH | Ana Mendoza | FALSE
EX-GEN-025 | Remote Sensing | Models (All) | Ejido Integration & Filtering | New Product Request | New Feature/Product Request | 2 | Medium | Open | The platform should incorporate ejido-level information for Amajac, EMSA, IPSA, into the database and make it available as a filter, allowing users—particularly supervisors—to filter and analyze data at the ejido level for improved segmentation and operational management. | 0% | 16/3/2026 |  | Web | Capacitación PSH | Ana Mendoza | FALSE
EX-GEN-026 | Remote Sensing | Smart Growth Index | Soil Moisture Integration (NDWI Alignment) | Data Accuracy | Issues and Bugs | 2 | Medium | Open | The soil moisture variable used in the Growth Index (SG) should be corrected by aligning it with the NDWI-derived moisture values, ensuring consistency between indices and improving the accuracy of the growth analysis. | 0% | 16/3/2026 |  | Web | Capacitación PSH | Ana Mendoza | FALSE
EX-GEN-027 | Remote Sensing | Models Home | Irrigation Priority & Water Stress Model | New Product Request | New Feature/Product Request | 2 | Critical | Open | The platform should include a new irrigation priority product focused on crop management. This product should integrate soil moisture percentage (%) and identify water stress conditions to support irrigation decision-making and optimize field management practices. | 0% | 16/3/2026 |  | Web | Capacitación PSH | Ana Mendoza | FALSE
EX-GEN-023 | Explore | Inspection | Location Capture / GPS Validation | Data Integration | Issues and Bugs | 1 | Critical | Open | In the mobile application, the location point for inspections should not be editable or movable by the user. The system should only allow capturing the current device location to ensure accuracy and reliability of georeferenced inspection data. | 0% | 17/3/2026 |  | Movil | Capacitación PSH | Ana Mendoza | FALSE
EX-GEN-024 | Explore | Inspection | Polygon Selection & Bulk Editing | New Product Request | New Feature/Product Request | 2 | Medium | Open | In the Field Operations (Labores) section, the interface should be interactive by displaying polygons that are selectable on the map. Users should be able to select one or multiple polygons and input or update data for all selected features simultaneously, enabling efficient bulk data entry and management. | 0% | 17/3/2026 |  | Movil | Capacitación PSH | Ana Mendoza | FALSE
EX-GEN-025 | Explore | Inspection | UI Layout / Responsive Design | Usability | Current Feature Enhancement | 2 | Critical | Open | In the mobile application, within the Inspection section, the interface does not properly adjust to the screen size. As a result, action buttons such as “Apply Changes” are partially hidden or overlapped, preventing users from interacting with them and completing the process. | 0% | 17/3/2026 |  | Movil | Capacitación PSH | Ana Mendoza | FALSE
EX-GEN-028 | Stomata-Home | Home | Session Tracking & Audit Logs | New Product Request | New Feature/Product Request | 2 | Medium | Open | The platform should implement PSH access monitoring, enabling user management by mill (Pantaleon, Monte Rosa, Amajac, IPSA, EMSA) and providing visibility into user sessions, including login activity by user and date, to support tracking, auditing, and usage analysis | 0% | 17/3/2026 |  | Web | Capacitación PSH | Ana Mendoza | FALSE
EX-GEN-026 | Explore | All Maps | Tile Generation / Resolution Handling | Data Quality | Issues and Bugs | 1 | Medium | Open | In IPSA, a resolution issue has been observed in the generation of map tiles, where the rendered imagery appears pixelated and inconsistent with the expected spatial resolution | 0% | 17/3/2026 |  | Movil | Capacitación PSH | Ana Mendoza | FALSE
RS-NDVI-004 | Remote Sensing | NDVI+ | Filter Logic & Naming Standardization | Data Consistency | Current Feature Enhancement | 1 | Critical | Open | In the NDVI Detailed Data by Parcel section, the Region and Quadrant filters are not applied correctly, as the data does not update according to the selected values. Additionally, there is inconsistency in the naming conventions across countries, which may lead to confusion and affect filtering and data interpretation. For example, in Amajac, IPSA, EMSA, values such as REGION_01, REGION1, REGION2, REGION_02 are displayed; in Pantaleon, REGION OESTE, REGION CENTRAL, REGION1, REGION_01; and in Monte Rosa, ZONA 1, PR, REGION7, REGION_07, among others. | 100% | 18/3/2026 |  | Web | Capacitación PSH | Ana Mendoza | FALSE
EX-GEN-029 | Remote Sensing | Models Home | KPI Summary Panel | New Product Request | New Feature/Product Request | 2 | Medium | Open | The dashboard should display a harvest performance summary at the time of data update, including key indicators such as productivity, number of fields, and hectares harvested (ha). | 0% | 18/3/2026 |  | Web | Capacitación PSH | Ana Mendoza | FALSE
GEOIA-CMM-012 | GEOIA Models | Cane Moisture Model | Country Context Mapping | Data Consistency | Current Feature Enhancement | 2 | Medium | Open | In Monte Rosa, when downloading the moisture TIFF, both in the platform and the API, the output incorrectly references GT instead of NI. This indicates an issue with the country or context identification in the export process, which may lead to confusion and incorrect data association. | 0% | 22/3/2026 |  | Web | Capacitación PSH | Ana Mendoza | FALSE

## Backlog
Module | Feature Area | Component | Issue Type | Priority | Severity | Classification | Description | Date Reported | Reference | Platform | Seguimiento | Solicitante | Aprobación

## Reference
REFERENCE DATA
Priority
1 – Critical | Must fix immediately
2 – High | Should fix soon
3 – Medium | Address in upcoming sprint
4 – Low | Nice to have
Severity
Critical | System unusable
High | Major function broken
Medium | Reduced function
Low | Minor issue
Status
Open | Not started
In Progress | Being worked on
In QA | Testing phase
Done | Resolved